## Sheet1
number	priority	type	status	description	note
3	1	bug	closed	animator: no undo/redo support for adding/removing objects	fixed
5	1	bug	closed	animator: no key-insert after camera zoom	fixed
6	1	bug	closed	animator: camera pans when camera-avatar is scaled	fixed
16	1	bug	closed	animator: edit model/camera/light doesn't work	fixed
30	1	bug	closed	animator: moving keys on multi-curve tracks causes other keys on that track to disappear	fixed
31	1	bug	closed	animator: moving a key on a multi-curve track past another key causes the first one to disappear	fixed
32	1	bug	open	Modeler: Deleting controlpoints sometimes does not remove a deleted controlpoint from selections (causing troubles when loading such a file).	won't fix in 0.5.3
33	1	bug	open	modeler: undoing add-bone does not reset the bone's pose. Deleting a bone has the same problem. Assign can't be undone too...
34	1	bug	closed	animator: scale doesn't work (creates 0 transformation matrix)	fixed
35	1	bug	open	Can't load old Jpatch models under Windows (?)	Not reproduceable, possibly Java6.0 only
37	1	bug	pending	jogl signatures need to be removed from jar file	needs to be done for every new jar file
40	1	bug	closed	Animator: scaling a selection in the timeline from the left side is buggy	fixed
45	1	bug	closed	modeler: bones can be attached to themself, resulting in stack-overflow	fixed
2	2	bug	closed	animator: no refresh after adding/removing objects	fixed
4	2	bug	closed	animator: no refresh after camera pan	fixed
8	2	bug	closed	animator: no refresh after manipulating model-dof in tree	fixed
10	2	bug	closed	modeler: not in edit morph mode after adding new morph	fixed
14	2	bug	closed	animator: tools not disabled in camera viewport	fixed
15	2	bug	closed	no show/don't show bones mode	fixed
19	2	bug	closed	point->bone assignment coloring can't be turned off	Turned off with “show bones”
25	2	feature	open	modeler: undo manager should intelligently combine some edits, e.g. changing tools after using the tool should be combined.
26	2	bug	open	Better error reporting when loading of a file fails
42	2	bug	closed	Modeler: Bones with 0 length can't be selected (and thus not be removed)	fixed: added delete/remove buttons to sidepanel
44	2	bug	closed	Still problems with keyboard focus: e.g. backspace when tree was highlighted	fixed???
47	2	bug	open	output to rib doesn't work (or does not output custom shaders)
48	2	bug	open	Animator becomes very slow with complex (i.e. many bones) models
7	3	bug	closed	animator: camera rotate tool has wrong size when camera was scaled	fixed
9	3	bug	open	animator: tools enabled during playback
17	3	bug	open	settings: updating some settings has no immediate effect (requires restart of jpatch) – which settings?
18	3	bug	closed	look and feel switching not saved in preferences	fixed
22	3	feature	open	lathe tool should treat points close to the y axis as if they were on the y axis
24	3	feature	open	animator: possibility to select all keys on given frames by selecting the frames on the ruler
27	3	feature	closed	animator: on tracks with multiple curves, clicking on a curve's name (in the track header) should bring that curve to front.	Implemented
28	3	feature	closed	animator: select objects from the tree	Implemented
29	3	feature	open	animator: select multiple objects at once	won't fix in 0.5.3
38	3	bug	open	modeler: align patches doesn't work optimally	won't fix in 0.5.3
39	3	feature	open	tesselation quality in settings should be combobox	Needs other fix (e.g. Separate dialog)
41	3	bug	closed	Modeler: Bones with 0 length can be inserted	fixed
43	3	bug	open	Clipping in software-zbuffer renderer doesn't work in perspective mode
46	3	bug	open	animator: when starting jpatch and software zbuffer is in use, the first repaint paints garbage and throws an exception
11	4	bug	closed	animator: zoom to fit does nothing	Zoom to fit button disabled
12	4	bug	closed	animator: x/y/z locks do not work	fixed
13	4	bug	closed	animator: hide, select points/bones, lock points/bones buttons not disabled	fixed
20	4	bug	open	animator: camera view menu not visible in main menu (only in the viewport popup)
23	4	bug	open	debugging output needs to be removed
36	4	bug	closed	when starting with commandline option –settings, splash doesn't disappear	fixed
1	5	bug	open	java2d renderer: repaint doesn't work after switching viewport modes, viewport initially stays gray
21	5	bug	open	Jpatch look and feel doesn't work on Java 6.0 (Mustang) beta