## Sheet1
number	priority	type	status	description	note
3	1	bug	pending	animator: no undo/redo support for adding/removing objects	fixed
5	1	bug	open	animator: no key-insert after camera zoom
6	1	bug	open	animator: camera pans when camera-avatar is scaled
16	1	bug	open	animator: edit model/camera/light doesn't work
30	1	bug	open	animator: moving keys on multi-curve tracks causes other keys on that track to disappear
31	1	bug	open	animator: moving a key on a multi-curve track past another key causes the first one to disappear
32	1	bug	open	Modeler: Deleting controlpoints sometimes does not remove a deleted controlpoint from selections (causing troubles when loading such a file).	won't fix in 0.5.3
33	1	bug	open	modeler: undoing add-bone does not reset the bone's pose
34	1	bug	pending	animator: scale doesn't work (creates 0 transformation matrix)	fixed
2	2	bug	open	animator: no refresh after adding/removing objects
4	2	bug	open	animator: no refresh after camera pan
8	2	bug	open	animator: no refresh after manipulating model-dof in tree
10	2	bug	open	modeler: not in edit morph mode after adding new morph
14	2	bug	open	animator: tools not disabled in camera viewport
15	2	bug	open	no show/don't show bones mode
19	2	bug	open	point->bone assignment coloring can't be turned off
23	2	bug	open	debugging output needs to be removed
25	2	feature	open	modeler: undo manager should intelligently combine some edits, e.g. changing tools after using the tool should be combined.
26	2	bug	open	Better error reporting when loading of a file fails
7	3	bug	open	animator: camera rotate tool has wrong size when camera was scaled
9	3	bug	open	animator: tools enabled during playback
17	3	bug	open	settings: updating some settings has no immediate effect (requires restart of jpatch)
18	3	bug	open	look and feel switching not saved in preferences
22	3	feature	open	lathe tool should treat points close to the y axis as if they were on the y axis
24	3	feature	open	animator: possibility to select all keys on given frames by selecting the frames on the ruler
27	3	feature	open	animator: on tracks with multiple curves, clicking on a curve's name (in the track header) should bring that curve to front.
28	3	feature	open	animator: select objects from the tree
29	3	feature	open	animator: select multiple objects at once	won't fix in 0.5.3
11	4	bug	open	animator: zoom to fit does nothing
12	4	bug	open	animator: x/y/z locks do not work
13	4	bug	open	animator: hide, select points/bones, lock points/bones buttons not disabled
20	4	bug	open	animator: camera view menu not visible in main menu (only in the viewport popup)
1	5	bug	open	java2d renderer: repaint doesn't work after switching viewport modes, viewport initially stays gray
21	5	bug	open	Jpatch look and feel doesn't work on Java 6.0 (Mustang) beta